## Workplan & Gnatt Chart
PROJECT NAME & Company Logo | [7 empty] | Week 01 | [6 empty] | Week 02 | [6 empty] | Week 03 | [6 empty] | Week 04 | [6 empty] | Week 05
Project Description | [11 empty] | TRUE
Start Date |  | 2026-01-10 | End Date | 2026-12-01 |  |  |  | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13
S/N | Activity | Description | Responsible Person | Key output | Start Date | End Date | Duration (Days) | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13
1 | Inception | Project Inception meeting | Project Manager | Make ppt | 2026-01-12 | 2026-01-12 | 1
2 | Baseline | Conduct Baseline Study | M&E Officer | Collect data | 2026-01-13 | 2026-01-30 | 18
3 | Baseline | Draft Baseline report | M&E Officer | Report 7 PPt | 2026-01-25 | 2026-02-02 | 9
4 | Engagement | Conduct project disclosure with leadership | Community Liaisons Officer | Report | 2026-01-18 | 2026-02-07 | 21
5 | Engagement | Engage leaders of existing Government programs | Community Liaisons Officer | Report | 2026-02-08 | 2026-02-20 | 13
6 | Workplans | Develop activty workplan & Budget | PM, M&E Officer | Workplan 7 Budget | 2026-01-01 | 2026-01-20 | 20
7 | Reporting | Compile Weekly Reports | M&E Officer | Report | 2026-01-12 | 2026-12-01 | 324
8 | Reporting | Compile Monthly Reports | M&E Officer | Report | 2026-01-12 | 2026-12-01 | 324
9 | Reporting | Compile Quartery Reports | M&E Officer | Report | 2026-01-12 | 2026-12-01 | 324
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
Show Weekends

## Instructions for Use
Activites | Instructions
Inception | Add all activities in your project in the under "Activites"
Baseline | Add your project name & Logo
Engagement | Add project start date; when your project started to have the Gnatt chart reflect it well
Workplans | You can insert columns between S/N & Start date in case you need another item included
Reporting | Only Insert new rows anywhere in the middle not at the end
Replace the exisiting data with your own information
When printing, all printing settings have been set for your ease. However. You can modify them to your preference
Print pdf and share with your team
Powered by: Soareth Agency Data Hub: www.soarethdatahub.com